{"text_format":"3","workbook":"xls","n_sheets":1,"sheets":["Sheet1"],"not_rendered":{"external_links":1,"defined_names":2},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Sheet1","index":0,"n_rows":7,"n_cols":6,"rows_kept":7,"merged":[[0,0,0,5]],"flags":["formulas_cached_only"]}
["开平市2024年中央财政衔接推进乡村振兴补助资金项目完成情况"]
["序号","项目类型","镇（街道）","省“百千万工程”典型村","建设内容","2024年项目完成情况"]
[1,"镇域公共服务类补短板项目","长沙街道","西溪村","维修及扩建朝东、朝西村道约410米，迁建朝东、朝西水机站。","维修及扩建朝东、朝西村道方面，施工已完工。迁建朝东、朝西水机站方面，水机站主体已建成，即将完工。接下来，跟进项目验收、项目资料收集和项目财政资金报账工作。"]
[2,"乡村产业项目","沙塘镇","红岭村","为盘活闲置资源，增加村集体经营性收入和带动村民就业，拟对闲置的红岭小学实施升级改造后再引入文旅项目。引入文旅项目后，预计通过出租和收益分成可以为村集体经营性收入增收约12万元/年。\n项目占地面积约530平方米，主要建设内容为对红岭小学进行加固补强约500平方米、防水补漏约530平方米、门窗升级改造（门22扇、窗91个）、消防系统改造约1100平方米、水电改造约1100平方米、墙面改造约2000平方米及小学周边风貌提升等。","已聘请第三方对红岭小学进行房屋可靠性检测鉴定，并进行房屋加固设计。目前正在施工方招投标阶段。"]
[3,"乡村产业项目（补改投）","赤坎镇","红溪村","赤坎镇红溪鹰村游客服务中心项目，利用红溪村委会鹰村内的闲置建设用地建设红溪鹰村游客服务中心，游客服务中心主要用于提供游客导游服务、农特产品售卖、咖啡简餐售卖空间等，建成后出租给鹰村田园综合体项目运营方，以增加集体经济收入。","红溪鹰村田园综合体已将规划用地通过“三资”管理平台以招拍挂形式租赁至投资方用于开发建设，已完成配套道路硬底化建设和旅游公厕建设，基本完成乡村咖啡馆室内改造，正进行居庐改造民宿项目以及餐厅建设。"]
[4,"镇域公共服务类补短板项目","赤水镇","沙洲村","村场硬底化1500平方，挡土墙200米；新建道路硬底化240米；新建3200米道路亮化工程，路灯150盏。","已全面开工建设，目前已完成70%，资金支付30%。"]
[5,"乡村产业项目","龙胜镇","桥新村","为桥新村村级厂房修建配套设施，包括宽5米，长约300多米的园区道路硬底化、排水设施、绿化改造等，建成后以租赁方式进行招商引资，该项目将为桥新村获取租金收益，预计年租金收入约20万元，并增加当地群众就近就业机会。","已全面开工建设，项目未完成"]